## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
Project ID: Car Servicing | <Batch code/project id> |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog <Bill Payment> Project ID: <HYD19IJ003/144> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
Req_1 | Task_1 | User Registration:Ability of the portal to procure user data and create new user profiles | Jaishree Baskar | 1 | 1 | [5 empty] | In-Progress
Req_2 | Task_1 | User Login:Ability of the portal to authenticate and authorize the registered user | Jaishree Baskar | 1 |  | 1 |  |  |  |  | In-Progress
Req_3 | Task_1 | Vendor Registration:Allows the vendor to register tehmselves | Jaishree Baskar | 1 |  | 1 |  |  |  |  | In-Progress
Req_4 | Task 1 | Admin:Admin should verify the vendor registration and approve to make the vendor active/deactive | Jaishree Baskar | 1 |  |  | 1 |  |  |  | In-Progress
Req_5 | Task_1 | Vendor Updation:Allows the vendor to edit, modify or delete the registered vendors available for online bill payments | Jaishree Baskar | 1 |  |  |  | 1 |  |  | In-Progress
|  | Total |  | 5 | 1 | 2 | 1 | 1 | 0 | 0
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog <Bill Payment> Project ID: <HYD19IJ003/144> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
Req_6 | Task_1 | Bill Payment:Allows the user to search for specific bill type and make the payment | Jaishree Baskar | 1 |  |  |  |  | 1 | 1 | In-Progress
Req_7 | Task_1 | Help:Page to assist the users to report technical issues | Jaishree Baskar | 1 | [5 empty] | 1 | In-Progress
|  | Total |  | 2 | 0 | 0 | 0 | 0 | 1 | 2
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A