## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Jaishree Baskar
| Role | Gen C
Signature
Date
Project ID: Car Servicing | <Batch code/project id> |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog Bill Payment Project ID: HYD19IJ003/144 C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
Req_1 | Task_1 | User Registration:Ability of the portal to procure user data and create new user profiles | Jaishree Baskar | 2 | 2 | [5 empty] | Completed
Req_2 | Task_1 | User Login:Ability of the portal to authenticate and authorize the registered user | Jaishree Baskar | 2 | 3 | [5 empty] | Completed
Req_3 | Task_1 | Spring Boot: Creating the 3-tier architecture for micro service for register/login. | Jaishree Baskar | 1 | 1 | [5 empty] | Completed
Req_4 | Task 1 | Database: Creating the necessary tables and linking database with the spring boot application | Jaishree Baskar | 2 | 2 | [5 empty] | Completed
Req_5 | Task_2 | Sprint Boot: Fetch vendor data from database and perform operations in the dao class to send only the newly registered vendors. | Jaishree Baskar | 6 |  | 7 |  |  |  |  | Completed
Req_6 | Task_2 | Admin Page : After authentication, displaying all the newly registered vendors to the admin. | Jaishree Baskar | 7 |  | 1 | 6 |  |  |  | Completed
Req_7 | Task_2 | Sprint Boot: Fetch vendor data from database and perform operations in the dao class to send all the registered vendors to the logged vendor. | Jaishree Baskar | 2 |  |  | 2 |  |  |  | Completed
Req_8 | Task_2 | Vendor Page: After authentication, displaying all the registered vendors to vendor page from spring boot also enabling edit and delete option to the logged vendor. With the condition such as logged vendor cannot delete himself. | Jaishree Baskar | 4 |  |  | 2 | 3 |  |  | Completed
Req_9 | Task_3 | Spring Boot: Fetch vendors data from the database and check the vendors accept status in the dao class. | Jaishree Baskar | 4 |  |  |  | 4 |  |  | Completed
Req_10 | Task_3 | Customer Page: Display the accepted vendors list from the spring to the angular forms and also enable a pay option for every accepted vendor. | Jaishree Baskar | 3 |  |  |  | 2 | 1 |  | Completed
Req_11 | Task_4 | Search Component: Enable a search bar for the logged user to pay the bill. This search is based on the vendor name/ bill type. | Jaishree Baskar | 3 |  |  |  |  | 4 |  | Completed
Req_12 | Task_5 | Customer Page: Create selective bill type form for paying the bill by the user when he clicks the pay button | Jaishree Baskar | 3 |  |  |  |  | 3 |  | Completed
Req_13 | Task_5 | Bill Payment Page: Once the user enters all the bill details and the payment method, the respective payment method form should be dispalyed. | Jaishree Baskar | 2 | [5 empty] | 2 | Completed
Req_14 | Task_5 | Bill Payment Page: Check all the details entered in the payment page is valid. If valid enable the pay option to the customer and display the payment successfully message. | Jaishree Baskar | 2 | [5 empty] | 2 | Completed
Req_15 | Task_6 | Test Cases: Creating and verifying all the test cases written for the authentication and user details. | Jaishree Baskar | 3 | [5 empty] | 3 | Completed
|  | Total |  | 46 | 8 | 8 | 10 | 9 | 8 | 7
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
|  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A